## Sheet1
EWA - ME462 Project Schedule
Activity | Start (Week) | End (Week) | Weeks
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Problem Definition | 1 | 4
Determination of Project Requirements | 2 | 5
Brainstorming | 3 | 5
Conceptual Design | 4 | 5
Best Concept Choice | 4 | 6
Proof of Concept | 8 | 14
Mechanical Design | 8 | 14
Control Software Development | 12 | 14
Main Software Development | 5 | 18
Test | 14 | 18