## Sheet1
EWA - ME462 Project Schedule
Activity | Start (Week) | End (Week) | Weeks
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Problem Definition | 1 | 4
Determination of Project Requirements | 2 | 5
Brainstorming | 3 | 5
Conceptual Design | 4 | 5
Best Concept Choice | 4 | 7
Proof of Concept | 8 | 15
Mechanical Design | 9 | 25
Control Software Development | 15 | 25
Main Software Development | 5 | 26
Test | 25 | 26
Note on E4: Melih: February 3 - February 9
Note on AB4: Melih: July 13 - July 19
Note on AC4: Melih: July 20 - July 26
Note on AD4: Melih: July 27 - August 2